## Prod Tasks SSM
Main Task Category | Task | Start Time | End Time | Skipped | WIP | Configured | Tested | Completed
Basic System Build | Branding and Color Scheme |  |  |  |  | x | x | x
Basic System Build | Attribute Labels |  |  |  | x
Basic System Build | SAML Configuration |  |  |  |  | x | x | x
Basic System Build | SMTP Configuration |  |  |  |  | x | x | x
Core Connection Setup/Check | AD User Domain |  |  |  |  | x | x | x
Core Connection Setup/Check | AD Admin User Domain |  |  |  |  | x | x | x
Core Connection Setup/Check | Workday Full user Import |  |  |  |  | x | x | x
Core Connection Setup/Check | Workday New Hire Import |  |  |  |  | x | x | x
Core Connection Setup/Check | Workday Termination |  |  |  |  | x | x | x
Core Connection Setup/Check | SOAP e-mail writeback |  |  |  |  | x | x | x
Core Connection Setup/Check | SAP ECC |  |  |  |  | x | x | x
Core Connection Setup/Check | SAP BW |  |  |  |  | x | x | x
Core Connection Setup/Check | Password Synchronization |  |  | x
Workday Data Validation | User Import |  |  |  |  | x | x | x
Workday Data Validation | Termination Import |  |  |  |  | x | x | x
Workday Data Validation | New Hire Import |  |  |  |  | x | x | x
Workday Data Validation | Workday (SOAP)- e-mail writeback |  |  |  |  | x
SOT (Workday) Onboarding | User Import |  |  |  | x
SOT (Workday) Onboarding | Attribute Mapping |  |  |  | x
SOT (Workday) Onboarding | e-mail mapping removal |  |  |  | x
SOT (Workday) Onboarding | Security System and Endpoint creation for "SOAP" writeback |  |  |  | x
AD Build | Security System and Endpoint (Admin User and User) |  |  |  |  | x | x | x
AD Build | User Import |  |  |  |  | x | x | x
AD Build | Attribute Mapping |  |  |  |  | x | x | x
AD Build | Account Correlation |  |  |  |  | x
AD Build | Import after Correlation |  |  | x
AD Build | Writeback testing |  |  | x
SAP Integration | Security System and Endpoint ECC |  |  |  |  | x
SAP Integration | Security System and Endpoint BW |  |  |  |  | x
SAP Integration | User Import |  |  |  | x
SAP Integration | Atribute Mapping |  |  |  |  | x
SAP Integration | Account Correlation |  |  |  |  | x | x | x
SAP Integration | Account Writeback |  |  |  |  | x
Specific Use Cases | DB Saviynt to Saviynt Configuration for "Mover/Term/SAV_Roles, etc" |  |  |  |  | x
Specific Use Cases | Saviynt to Saviynt (DB) connection to manage "SAP" account name change usecase |  |  |  |  | x
Configuration | Global Configuration |  |  |  | x
Configuration | Connector checking (Preprocessing, etc.) |  |  |  | x
Configuration | Enterprise Roles |  |  |  | x
Configuration | Technical Rules |  |  |  | x
Configuration | User Update Rules |  |  |  | x
Configuration | Workflow |  |  |  | x
Configuration | E-mail template |  |  |  | x
Configuration | Job Control Panel |  |  |  | x
Administration | Admin User Provisioning |  |  |  |  | x | x | x
Administration | SAV_ROLE configuration |  |  |  |  | x | x | x
High-Level Use Case Testing by Saviynt | SSO by User (WIP, but not working) |  |  |  | x
High-Level Use Case Testing by Saviynt | Workday User import |  |  |  | x
High-Level Use Case Testing by Saviynt | New Hire |  |  |  | x
High-Level Use Case Testing by Saviynt | Rehire |  |  |  | x
High-Level Use Case Testing by Saviynt | Mover |  |  |  | x
High-Level Use Case Testing by Saviynt | Termination |  |  |  | x
High-Level Use Case Testing by Saviynt | Account Provisioning in AD-User |  |  |  | x
High-Level Use Case Testing by Saviynt | Account request in AD-Admin User |  |  |  | x
High-Level Use Case Testing by Saviynt | SAP BW and ECC |  |  |  | x
High-Level Use Case Testing by Saviynt | SAP BW and ECC request |  |  |  | x
High-Level Use Case Testing by Saviynt | Password Sync |  |  |  | x
High-Level Use Case Testing by Saviynt | E-mail template |  |  |  | x
High-Level Use Case Testing by Saviynt | SAV_ROLES |  |  |  | x
High-Level Use Case Testing by Saviynt | Request testing |  |  |  | x
Pre Go-Live | DB Snapshot |  |  | x
Pre Go-Live | Synchronization Schedule configuration (Workday jobs) |  |  | x
Pre Go-Live | AD Sync Schedule |  |  | x
Pre Go-Live | SAP Sync Schedule |  |  | x
Pre Go-Live | Analytics Reporting |  |  | x
Pre Go-Live | Dashboard. |  |  | x
Pre Go-Live | Client Specific Rules |  |  | x
Controlled Live | - |  |  | x
Go Live Cutover | - |  |  | x
Hypercare | - |  |  | x
UAT Support and Documentation | - |  |  | x